## Sheet1
Phase | Task | Start Date | Target Completion | Owner | Status | Remarks
Phase 1 (MVP – 15 Days) | Flight Booking (TripJack API) | 23-Aug-2025 | 25-Aug-2025 | Emergent | Completed | Flight search, booking flow, Tripjack API integration with real pricing data. PostgreSQL migration completed.
Phase 1 (MVP – 15 Days) | Hotel Booking (TripJack API) | 23-Aug-2025 | 07-Sep-2025 | Emergent | In Progress | Basic hotel search implemented. Full TripJack hotel booking integration 80% complete.
Phase 1 (MVP – 15 Days) | Basic TourBuilder (flights + hotels) | 23-Aug-2025 | 25-Aug-2025 | Emergent | Completed | Auto flight+hotel packages, transparent pricing, duration filters (2N/3D-6N/7D), budget tiers (economy/premium/luxury), 10 destinations integrated.
Phase 1 (MVP – 15 Days) | OTP Authentication (MSG91) | 23-Aug-2025 | 25-Aug-2025 | Emergent | Completed | OTP send/verify, user registration/login, sandbox testing ready. MSG91 integration framework complete, awaiting credentials.
Phase 1 (MVP – 15 Days) | Simple Admin Dashboard | 23-Aug-2025 | 07-Sep-2025 | Emergent | Pending | Database and backend APIs ready. Frontend dashboard development remaining.
Phase 2 (Month 2–3) | Viator API Integration | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 2 (Month 2–3) | Wallet/Credits System | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 2 (Month 2–3) | Expanded CMS (banners, FAQs, promos) | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 2 (Month 2–3) | Role-based Staff Panel | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 3 (Month 4–6) | AI Chatbot (OpenAI) | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 3 (Month 4–6) | WhatsApp Business API | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 3 (Month 4–6) | Analytics Dashboard | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 3 (Month 4–6) | CRM Lite (client folio, reminders) | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Pan-India Expansion | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Loyalty Program | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Multiple Supplier APIs (TripJack + TBO) | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Scaling Infrastructure (AWS/GCP) | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started
Phase 1 (MVP – 15 Days) | PostgreSQL + Redis Migration | 24-Aug-2025 | 25-Aug-2025 | Emergent | Completed | Complete database migration from MongoDB to PostgreSQL with Redis caching. 6 tables created with comprehensive schema.
Phase 1 (MVP – 15 Days) | Razorpay Payment Integration | 25-Aug-2025 | 25-Aug-2025 | Emergent | Completed | Full payment gateway with order creation, verification, webhooks, refunds. Sandbox testing ready. Multiple payment methods supported.
Phase 1 (MVP – 15 Days) | Waitlist System with Location Tracking | 24-Aug-2025 | 24-Aug-2025 | Emergent | Completed | Email capture, geographic analytics, admin notifications, PostgreSQL integration completed.
PROJECT SUMMARY
| Phase 1 Progress: | 67% Complete (4/6 core tasks)
| Completed Tasks: | 6 |  |  |  | Flight Booking, TourBuilder, OTP Auth, Database Migration, Payments, Waitlist
| In Progress: | 1 |  |  |  | Hotel Booking (80% complete)
| Pending: | 1 |  |  |  | Admin Dashboard
| Total API Endpoints: | 25+ |  |  |  | TourBuilder, Payments, Auth, Waitlist, Flights, Hotels
| Database: | PostgreSQL + Redis |  |  |  | 6 tables, comprehensive schema
| Payment Gateway: | Razorpay Sandbox Ready |  |  |  | Multiple payment methods integrated
| Authentication: | OTP-based (MSG91 Ready) |  |  |  | User registration/login functional
| Package Generation: | Intelligent TourBuilder |  |  |  | Auto flight+hotel packages with pricing tiers
| Next Priorities: | Hotel Integration, Admin Dashboard |  |  |  | Complete Phase 1 remaining tasks