## Sheet1
Phase | Task | Start Date | Target Completion | Owner | Status | Remarks
Phase 1 (MVP – 15 Days) | Flight Booking (TripJack API) | 23-Aug-2025 | 07-Sep-2025 | Emergent | Not Started
Phase 1 (MVP – 15 Days) | Hotel Booking (TripJack API) | 23-Aug-2025 | 07-Sep-2025 | Emergent | Not Started
Phase 1 (MVP – 15 Days) | Basic TourBuilder (flights + hotels) | 23-Aug-2025 | 07-Sep-2025 | Emergent | Not Started
Phase 1 (MVP – 15 Days) | OTP Authentication (MSG91) | 23-Aug-2025 | 07-Sep-2025 | Emergent | Not Started
Phase 1 (MVP – 15 Days) | Simple Admin Dashboard | 23-Aug-2025 | 07-Sep-2025 | Emergent | Not Started
Phase 2 (Month 2–3) | Viator API Integration | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 2 (Month 2–3) | Wallet/Credits System | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 2 (Month 2–3) | Expanded CMS (banners, FAQs, promos) | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 2 (Month 2–3) | Role-based Staff Panel | 08-Sep-2025 | 07-Nov-2025 | Emergent | Not Started
Phase 3 (Month 4–6) | AI Chatbot (OpenAI) | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 3 (Month 4–6) | WhatsApp Business API | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 3 (Month 4–6) | Analytics Dashboard | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 3 (Month 4–6) | CRM Lite (client folio, reminders) | 08-Nov-2025 | 06-Feb-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Pan-India Expansion | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Loyalty Program | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Multiple Supplier APIs (TripJack + TBO) | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started
Phase 4 (Month 6–12) | Scaling Infrastructure (AWS/GCP) | 07-Feb-2026 | 06-Aug-2026 | Emergent | Not Started